## Sheet1
RICE ID | Object Name | Object Type | Progress % | Status | Files Used | Resource Names | Description | Start Date | Target Date
R-001 | iProcurement Requisition Status Report | REPORT | 75 | IN_PROGRESS | XXPO_IPROC_REQ_STATUS_RPT.rdf, XXPO_IPROC_REQ_STATUS_PKG.pks, XXPO_IPROC_REQ_STATUS_PKG.pkb, XXPO_IPROC_REQ_STATUS_RPT.xml | Rajesh Kumar, Priya Sharma | Custom report showing iProcurement requisition status with approval hierarchy and buyer assignments | 2026-04-01 | 2026-05-30
I-002 | PO to External Vendor System Interface | INTERFACE | 45 | IN_PROGRESS | XXPO_VENDOR_INT_PKG.pks, XXPO_VENDOR_INT_PKG.pkb, XXPO_VENDOR_INT_STG.sql, XXPO_VENDOR_INT_CONC.prog, vendor_interface_mapping.xml | Amit Patel, Sneha Reddy | Outbound interface to send PO data to external vendor portal via REST API | 2026-03-15 | 2026-06-15
C-003 | Legacy Supplier Data Migration | CONVERSION | 90 | TESTING | XXPO_SUPPLIER_CONV_STG.sql, XXPO_SUPPLIER_CONV_PKG.pks, XXPO_SUPPLIER_CONV_PKG.pkb, XXPO_SUPPLIER_CONV_VAL.sql, supplier_migration_test_cases.xlsx | Rajesh Kumar, Vikram Singh | One-time conversion to migrate supplier master data from legacy system to AP_SUPPLIERS and PO_VENDORS | 2026-02-01 | 2026-05-20
E-004 | Custom Account Generator for PO | ENHANCEMENT | 30 | BLOCKED | XXPO_CUSTOM_ACCT_GEN_PKG.pks, XXPO_CUSTOM_ACCT_GEN_PKG.pkb, XXPO_ACCT_GEN_RULES.sql, po_account_generator_setup.doc | Priya Sharma | Custom workflow account generator to derive GL accounts based on item category location and cost center for PO distributions | 2026-04-20 | 2026-07-01
E-005 | Custom AP Invoice Validation Rules | ENHANCEMENT | 100 | COMPLETED | XXAP_INVOICE_VALIDATION_PKG.pks, XXAP_INVOICE_VALIDATION_PKG.pkb, XXAP_CUSTOM_VALIDATIONS.sql, ap_validation_rules_config.xlsx | Amit Patel | Custom validation rules for AP invoices including tolerance checks duplicate invoice detection and mandatory field validations | 2026-01-10 | 2026-04-30